## About
Created on: | 16 Dec 23 20:35 UTC
Jira Site: | https://lolcgroupdev.atlassian.net
Jira Query: | project = PF AND issuetype = Epic AND "Story Points[Number]" > "0" order by created DESC

## sheet01
Issue Type | Key | Summary | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Due date | Sprint | Time Spent | Σ Time Spent | Original estimate | Remaining Estimate | Σ Original Estimate | Σ Remaining Estimate | Project | Labels | Story Points
Epic | PF-3158 | Account Module ¦ Finance GL Account Mapping ¦ Mapping GL Level separately for Current Account and Savings Accounts ¦ Developing a new Functionality |  | BandulaR | High | To Do |  | 2023-12-13 10:15 | 2023-12-13 22:51 | [6 empty] | 28800 | 28800 | Product FusionX | AccountsModule;BA_DEC_2;ClientKenya | 48
Epic | PF-3000 | Lending Module ¦ Excess Duty ¦ Calculate Tax ¦ Modification to the Existing Function | Dinesh Wickramaarachchi | Gihan Abeykoon[IT/EKO/LOITS] | Highest | To Do |  | 2023-12-10 23:28 | 2023-12-14 17:21 | [6 empty] | 115200 | 115200 | Product FusionX | BA_DEC_2;ClientKenya;LendingModule | 120
Epic | PF-2999 | Lending Module ¦ Reports ¦ Business Reporting ¦ Developing a new Report | Dinesh Wickramaarachchi | Gihan Abeykoon[IT/EKO/LOITS] | Medium | To Do |  | 2023-12-10 23:27 | 2023-12-14 18:03 | [6 empty] | 115200 | 115200 | Product FusionX | BA_JAN_1;ClientKenya;LendingModule | 304
Epic | PF-2996 | Lending Module ¦ Charges ¦ Vehicle Tracker Operation ¦ Developing a new Functionality |  | Gihan Abeykoon[IT/EKO/LOITS] | Highest | To Do |  | 2023-12-10 23:22 | 2023-12-14 17:14 | [6 empty] | 115200 | 115200 | Product FusionX | BA_JAN_1;ClientKenya;LendingModule | 192
Epic | PF-2995 | Lending Module ¦ Charges ¦ Charges wave off on disbursement ¦ Developing a new Functionality |  | Gihan Abeykoon[IT/EKO/LOITS] | Medium | To Do |  | 2023-12-10 23:16 | 2023-12-14 17:42 | [6 empty] | 115200 | 115200 | Product FusionX | BA_JAN_1;ClientKenya;LendingModule | 288
Epic | PF-2994 | Lending Module ¦ Proceeds Handling ¦ Loan settlement from Loan disbursement ¦ Developing a new Functionality |  | Gihan Abeykoon[IT/EKO/LOITS] | Medium | To Do |  | 2023-12-10 23:14 | 2023-12-14 17:38 | [6 empty] | 115200 | 115200 | Product FusionX | BA_JAN_1;ClientKenya;LendingModule | 240
Epic | PF-2993 | Lending Module ¦ Proceeds Handling ¦ Payment of Loan Proceeds to a Third Party ¦ Developing a new Functionality | Dinesh Wickramaarachchi | Gihan Abeykoon[IT/EKO/LOITS] | Medium | To Do |  | 2023-12-10 23:12 | 2023-12-14 17:33 | [6 empty] | 86400 | 86400 | Product FusionX | BA_JAN_1;ClientKenya;LendingModule | 192
Epic | PF-2789 | Lending Module ¦ Receipt Allocation (Prior to the Appraisal) ¦ Developing a new Functionality |  | Gihan Abeykoon[IT/EKO/LOITS] | Medium | To Do |  | 2023-12-07 17:41 | 2023-12-14 17:54 | [6 empty] | 57600 | 57600 | Product FusionX | BA_JAN_1;ClientKenya;LendingModule | 120
Epic | PF-2724 | Account Module ¦ Transaction Reference & Statement Reference ¦ New UI Development | VivekaI | Gihan Abeykoon[IT/EKO/LOITS] | Highest | To Do |  | 2023-12-06 19:09 | 2023-12-14 23:03 | [6 empty] | 57600 | 57600 | Product FusionX | AccountsModule;BA_DEC_2;product | 24
Epic | PF-2720 | Account Module ¦ Manage Account ¦ Transaction Inquiry ¦ UI Enhancement | Gihan Abeykoon[IT/EKO/LOITS] | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-12-06 18:45 | 2023-12-13 22:06 | [8 empty] | Product FusionX | AccountsModule;product | 112
Epic | PF-2715 | Account Module ¦ Manage Account ¦ Search By Customer Details ¦ Include Additional Search Criteria |  | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-12-06 16:26 | 2023-12-12 22:48 | [8 empty] | Product FusionX | AccountsModule;product | 40
Epic | PF-2540 | TD Module ¦ Enable Tool Tips ¦ Developing a new Functionality |  | Gihan Abeykoon[IT/EKO/LOITS] | Highest | To Do |  | 2023-12-04 23:56 | 2023-12-12 22:52 |  |  |  | 28800 |  |  | 129600 | 100800 | Product FusionX | BA_DEC_2;FDModule;product | 50
Epic | PF-2526 | Home Page ¦ Enable Chat GPT Link ¦ Developing a new Functionality | rajitha kumara | Gihan Abeykoon[IT/EKO/LOITS] | Highest | To Do |  | 2023-12-04 23:26 | 2023-12-13 22:43 |  |  |  | 28800 |  |  | 43200 | 14400 | Product FusionX | BA_DEC_2;HomePage;product | 36
Epic | PF-2462 | Common ¦ Reports and Settings ¦ Naming Conversion for all the reports ¦ Modification for Existing Reports |  | Gihan Abeykoon[IT/EKO/LOITS] | Highest | To Do |  | 2023-12-04 13:21 | 2023-12-15 00:15 | [6 empty] | 158400 | 158400 | Product FusionX | BA_DEC_2;commonTasks;product | 4
Epic | PF-2358 | Lending Module ¦ Loan Management ¦ Loan Finance ¦ Scheduler Charges Debits for Loans ¦ Developing a New Functionality | Dinesh Wickramaarachchi | Asitha Abeysekara | Highest | To Do |  | 2023-12-01 10:23 | 2023-12-12 22:32 | [6 empty] | 115200 | 115200 | Product FusionX | BA_DEC_2;ClientKenya;LendingModule | 288
Epic | PF-2345 | Lending Module ¦ Loan Management ¦ Loan Finance ¦ Loan Charges Payable Confirmation (Loan Charges where the collection type is Third-party) ¦ Developing a new Functionality | Dinesh Wickramaarachchi | Asitha Abeysekara | Medium | To Do |  | 2023-12-01 09:20 | 2023-12-14 17:59 | [6 empty] | 115200 | 115200 | Product FusionX | BA_JAN_1;ClientKenya;LendingModule | 240
Epic | PF-2147 | Lending Module ¦ Follow up Blocker, Bugs, and Incomplete Developments in Phase 01 | Dinesh Wickramaarachchi | Asitha Abeysekara | Medium | Abandoned |  | 2023-11-28 16:55 | 2023-12-15 00:25 | [8 empty] | Product FusionX | LendingModule;product | 450
Epic | PF-2146 | Account Module ¦ Customer Management ¦ E-KYC integration and Customer On-Boarding ¦ Developing a new Functionality | BandulaR | BandulaR | Highest | In Definition |  | 2023-11-28 16:52 | 2023-12-12 22:48 | [8 empty] | Product FusionX | AccountsModule;product | 104
Epic | PF-2142 | Account Management ¦ Overdraft Management ¦ Overdraft Balance Write-off ¦ Developing a new Functionality | BandulaR | BandulaR | Highest | In Definition |  | 2023-11-28 16:25 | 2023-12-13 15:45 |  |  |  | 57600 |  |  | 86400 | 57600 | Product FusionX | AccountsModule;BA_DEC_1;product | 248
Epic | PF-2137 | Account Management ¦ Overdraft Management ¦ Overdraft Account Balance Transfer ¦ Developing a new Functionality | BandulaR | BandulaR | Highest | In Definition |  | 2023-11-28 16:12 | 2023-12-13 15:53 | [6 empty] | 72000 | 72000 | Product FusionX | AccountsModule;BA_DEC_1;product | 224
Epic | PF-2135 | Account Module ¦ Over Draft Management ¦ Casual Overdraft Facility Management ¦ Developing a new Functionality | BandulaR | BandulaR | Highest | In Definition |  | 2023-11-28 15:54 | 2023-12-15 15:37 |  |  |  | 82800 |  |  | 115200 | 32400 | Product FusionX | AccountsModule;BA_DEC_1;product | 150
Epic | PF-2111 | Lending Module ¦ Report ¦ Internal Report ¦ Trial Calculation Report ¦ Developing a New Report | Dinesh Wickramaarachchi | Asitha Abeysekara | Highest | In Definition |  | 2023-11-28 14:00 | 2023-12-12 22:32 |  |  |  | 7200 |  |  | 72000 | 64800 | Product FusionX | BA_DEC_1;LendingModule;product | 24
Epic | PF-2109 | Lending Module ¦ Loan Management ¦ Loan Administration ¦ Update the Recovery Account ¦ Developing a new Functionality | Dinesh Wickramaarachchi | Asitha Abeysekara | Medium | Abandoned | Done | 2023-11-28 13:45 | 2023-12-11 00:06 |  |  |  | 7200 |  |  | 72000 | 64800 | Product FusionX |  | 40
Epic | PF-2108 | Lending Module ¦ BE Processes¦ Loan Finance ¦ Calculate Daily Interest for EMI Loans ¦ Developing a new Functionality | Dinesh Wickramaarachchi | Asitha Abeysekara | Highest | In Definition |  | 2023-11-28 13:32 | 2023-12-15 16:47 |  |  |  | 3600 |  |  | 72000 | 68400 | Product FusionX | BA_DEC_1;ClientKenya;LendingModule;product | 200
Epic | PF-2107 | Lending Module ¦ Loan Origination ¦ Loan Creation ¦ Flat Rate Incorporation in TC ¦ Developing a new Functionality | Dinesh Wickramaarachchi | Asitha Abeysekara | Highest | In Definition |  | 2023-11-28 13:31 | 2023-12-14 09:14 |  |  |  | 39600 |  |  | 72000 | 32400 | Product FusionX | BA_DEC_1;ClientKenya;LendingModule;product | 160
Epic | PF-2095 | Lending Module ¦ Settings ¦ Recovery ¦ Recovery Integration (Afinity) | Dinesh Wickramaarachchi | Asitha Abeysekara | Highest | In Definition |  | 2023-11-28 13:08 | 2023-12-14 20:44 | [8 empty] | Product FusionX | BA_DEC_2;ClientKenya;LendingModule | 240
Epic | PF-1737 | Account ¦ Product ¦ Cash buildup ¦ Developing a new Functionality | Sampath Dimuthu Gallage | Gihan Abeykoon[IT/EKO/LOITS] | Highest | To Do |  | 2023-11-23 23:19 | 2023-12-12 11:24 | [6 empty] | 43200 | 43200 | Product FusionX | AccountsModule;BA_DEC_1;ClientZambia;product | 28
Epic | PF-1375 | TD Module ¦ Account Management ¦ Open Account ¦ Link TD with a loan while opening TD (Cash Backed Facility) ¦ Developing a new Functionality | Randika Gunasekara | Gihan Abeykoon[IT/EKO/LOITS] | Highest | To Do |  | 2023-11-16 16:27 | 2023-12-15 00:34 | [6 empty] | 115200 | 115200 | Product FusionX | BA_DEC_1;TD_Module;product | 28
Epic | PF-1049 | COB ¦ Initiate Workflow ¦ Sensitive Information Approval (COMMON) ¦ Developing a new Functionality | MilleniN | Gihan Abeykoon[IT/EKO/LOITS] | Highest | In Definition |  | 2023-11-10 17:08 | 2023-12-12 22:52 | [6 empty] | 43200 | 43200 | Product FusionX | BA_DEC_1;CustomerOnBoardingModule;product | 28
Epic | PF-901 | Yard Module ¦ Automation Comments Management ¦ Developing a new Functionality | Gihan Abeykoon[IT/EKO/LOITS] | Gihan Abeykoon[IT/EKO/LOITS] | Highest | To Do |  | 2023-11-09 12:25 | 2023-12-13 10:11 |  |  |  | 14400 |  |  | 43200 | 28800 | Product FusionX | BA_DEC_1;LOFIN;YardModule | 12
Epic | PF-900 | Yard Module ¦ Debit Valuation charges Automatically ¦ Developing a new Functionality | Gihan Abeykoon[IT/EKO/LOITS] | Gihan Abeykoon[IT/EKO/LOITS] | Highest | To Do |  | 2023-11-09 12:24 | 2023-12-15 14:48 |  |  |  | 36000 |  |  | 72000 | 36000 | Product FusionX | BA_DEC_1;LOFIN;YardModule | 16
Epic | PF-899 | Yard Module ¦ Upload Valuation Bulk Wise ¦ Developing a new Functionality | Gihan Abeykoon[IT/EKO/LOITS] | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-11-09 12:22 | 2023-12-14 10:17 |  |  |  | 57600 |  |  | 28800 | 0 | Product FusionX | BA_DEC_1;LOFIN;YardModule | 96
Epic | PF-890 | Yard Module ¦ Reports ¦ Yard Detail Report ¦ Developing a New Report | MilleniN | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-11-09 11:53 | 2023-12-13 11:34 |  |  |  | 32400 |  |  | 43200 | 10800 | Product FusionX | BA_DEC_1;LOFIN;YardModule | 8
Epic | PF-586 | Lending Module ¦ Loan Account Management ¦ Account Maintenance ¦ Contract Approval History Maintenance ¦ Developing a new inquiry Details. | Dinesh Wickramaarachchi | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-11-08 02:11 | 2023-12-12 22:32 |  |  |  | 100800 |  |  | 100800 | 0 | Product FusionX | BA_NOV_1;LendingModule;product | 60
Epic | PF-578 | Common Settings Module ¦ Document Template Management ¦ Document Repository Maintenance ¦ Developing a new Functionality | Dinuja Theeraj | Gihan Abeykoon[IT/EKO/LOITS] | Highest | In Definition |  | 2023-11-08 01:35 | 2023-12-12 22:32 |  |  |  | 100800 |  |  | 100800 | 0 | Product FusionX | BA_NOV_2;LendingModule;UI/UX_Pending;product | 224
Epic | PF-577 | Common Settings Module ¦ Document Template Management ¦ Document Fields Mapping ¦ Developing a new Functionality | rajitha kumara | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-11-08 01:34 | 2023-12-12 22:32 |  |  |  | 72000 |  |  | 100800 | 28800 | Product FusionX | BA_DEC_1;LendingModule;product | 12
Epic | PF-572 | Lending Module ¦ Loan Origination ¦ Credit Appraisal ¦ Refresh the updated details according to the COB data update | Dinesh Wickramaarachchi | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-11-07 18:02 | 2023-12-12 22:32 |  |  |  | 100800 |  |  | 100800 | 0 | Product FusionX | BA_NOV_2;LendingModule;UI/UX_Pending;product | 308
Epic | PF-559 | Lending Module ¦ Account Management ¦ Account Inquiry ¦ Account Details ¦Developing UI Changes | Dinesh Wickramaarachchi | Gihan Abeykoon[IT/EKO/LOITS] | Highest | In Definition |  | 2023-11-07 15:27 | 2023-12-14 15:45 | [6 empty] | 28800 | 28800 | Product FusionX | BA_DEC_1;LendingModule;UI/UX_Pending;product | 480
Epic | PF-539 | Common Settings Module ¦ Document Template Management ¦ Letter Type Definition ¦ Developing a new Functionality | Sampath Dimuthu Gallage | Sampath Dimuthu Gallage | Highest | Ready for Development |  | 2023-11-07 10:46 | 2023-12-12 22:32 |  |  |  | 14400 |  |  | 43200 | 28800 | Product FusionX | BA_NOV_1;LendingModule;product | 68
Epic | PF-301 | Lending Module ¦ Settings ¦ Bad Debt Provisions (NPL & IIS) ¦ Bad Debt Provision Buckets ¦ Developing a new Functionality | Dinesh Wickramaarachchi | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-10-27 01:08 | 2023-12-12 22:32 |  |  |  | 57600 |  |  | 86400 | 28800 | Product FusionX | BA_OCT_3;LendingModule;product | 836
Epic | PF-298 | Lending Module ¦ Loan Account Management ¦ Account Maintenance ¦ Loan GL Reconciliation ¦ Developing a new Functionality | Dinesh Wickramaarachchi | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-10-27 00:58 | 2023-12-12 22:32 |  |  |  | 86400 |  |  | 86400 | 0 | Product FusionX | BA_NOV_1;LendingModule;product | 80
Epic | PF-277 | Lending Module ¦ Loan Account Management ¦ Asset Change ¦ Asset Change Request ¦ Developing a new Functionality | Dinesh Wickramaarachchi | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-10-26 23:26 | 2023-12-12 22:32 |  |  |  | 57600 |  |  | 57600 | 0 | Product FusionX | LeasingModule;LendingModule;product | 224
Epic | PF-275 | Lending Module ¦ Transaction ¦ Approve Supplier Payables ¦ Developing a new Functionality | Dinesh Wickramaarachchi | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-10-26 23:25 | 2023-12-12 22:32 |  |  |  | 72000 |  |  | 72000 | 0 | Product FusionX | BA_OCT_3;Estimation_pending;LeasingModule;LendingModule;product | 96
Epic | PF-273 | Lending Module ¦ Loan Account Management ¦ Account Maintenance ¦ Change Payee ¦ Developing a new Functionality | Chamin Vihanga | Gihan Abeykoon[IT/EKO/LOITS] | Highest | In Definition |  | 2023-10-26 23:20 | 2023-12-12 22:32 |  |  |  | 100800 |  |  | 216000 | 115200 | Product FusionX | BA_NOV_2;LeasingModule;LendingModule;UI/UX_Pending;product | 212
Epic | PF-272 | Lending Module ¦ Introducer Payment/Commission (Trigger) ¦ Developing a new Functionality | Chamin Vihanga | Gihan Abeykoon[IT/EKO/LOITS] | Highest | In Definition |  | 2023-10-26 23:19 | 2023-12-14 17:58 |  |  |  | 100800 |  |  | 100800 | 0 | Product FusionX | BA_DEC_2;LeasingModule;LendingModule;product | 240
Epic | PF-271 | Lending Module_ Manage Purchase Order | Asitha Abeysekara | Gihan Abeykoon[IT/EKO/LOITS] | Medium | In Definition |  | 2023-10-26 23:19 | 2023-12-13 15:54 |  |  |  | 115200 |  |  | 201600 | 86400 | Product FusionX | BA_OCT_3;LeasingModule;LendingModule;UI/UX_Pending;product | 208
Epic | PF-270 | Lending Module ¦ Loan Account Management ¦ Account Maintenance ¦ Accept Charges after the lead Creation ¦ Developing a new Functionality | Dinesh Wickramaarachchi | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-10-26 23:17 | 2023-12-12 22:32 |  |  |  | 151200 |  |  | 100800 | 0 | Product FusionX | BA_NOV_2;LeasingModule;LendingModule;product | 266
Epic | PF-262 | COB Module ¦ Customer Onboarding ¦ Customer Employment Status ¦ Developing a new Functionality | MilleniN | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-10-26 12:44 | 2023-12-12 22:52 |  |  |  | 144000 |  |  | 172800 | 28800 | Product FusionX | BA_NOV_1;ClientZambia;CustomerOnBoardingModule | 4
Epic | PF-251 | TD Module & Account Module ¦ Account Management ¦ Manage Account ¦ Account Inquiry ¦ Include Summary detail into the Information Bar | BhagyaA | Gihan Abeykoon[IT/EKO/LOITS] | Highest | In Definition |  | 2023-10-26 10:25 | 2023-12-12 22:48 |  |  |  | 172800 |  |  | 57600 | 0 | Product FusionX | AccountsModule;BA_DEC_1;product | 74
Epic | PF-246 | Account Module ¦ Transaction ¦ Disbursement Payment Process ¦ Modify the Entry Generation Process | MilleniN | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-10-26 09:44 | 2023-12-12 22:52 |  |  |  | 57600 |  |  | 187200 | 129600 | Product FusionX | AccountsModule;BA_NOV_1;ClientZambia | 32
Epic | PF-1169 | Accounts Module_Alerts Generation | Janaka Abesinghe [IT/EKO/LOITS] | Gihan Abeykoon[IT/EKO/LOITS] | Highest | In UAT | Done | 2023-10-19 14:30 | 2023-12-13 11:23 |  |  |  | 907200 |  |  | 244800 | 0 | Product FusionX | AccountsModule;KenyaDecember2023;Nov_2 | 217
Epic | PF-35 | TD Module ¦ Account Management ¦ Opening Account ¦ Enable Back Value Dated & Future Value Dated account opening | BhagyaA | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-10-18 20:53 | 2023-12-12 22:52 |  |  |  | 100800 |  |  | 100800 | 0 | Product FusionX | BA_NOV_1;FDModule;product | 96
Epic | PF-33 | TD Module ¦ Account Management ¦ Opening Account ¦ TD clone (Copy) ¦ Developing a new Functionality | Dinuja Theeraj | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-10-18 20:52 | 2023-12-12 22:52 |  |  |  | 100800 |  |  | 100800 | 0 | Product FusionX | BA_NOV_1;FDModule;product | 72
Epic | PF-32 | TD Module ¦ Account Management ¦ Returning the FD Creation ¦ Developing a new Functionality | Gihan Abeykoon[IT/EKO/LOITS] | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-10-18 20:51 | 2023-12-14 09:33 |  |  |  | 100800 |  |  | 115200 | 14400 | Product FusionX | FDModule;UI/UX_Pending;product | 290
Epic | PF-30 | TD Module ¦ Transfer Ownership ¦ Developing a new Functionality | BhagyaA | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-10-18 20:51 | 2023-12-12 22:52 |  |  |  | 194400 |  |  | 136800 | 0 | Product FusionX | BA_NOV_1;FDModule;product | 616
Epic | PF-14 | All Modules ¦ Settings ¦ Product Definition ¦ Approval Function for Product Creation ¦ Develop Dual Control | Naveen Rathnayake | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-10-18 13:48 | 2023-12-12 22:52 |  |  |  | 100800 |  |  | 100800 | 0 | Product FusionX | BA_NOV_1;ProductSettings;product | 382
Epic | PF-709 | Collateral Module ¦ Collateral Onboarding ¦ Inspection & Valuation ¦ Display/View Added Documents | Naveen Rathnayake | Naveen Rathnayake | Highest | Ready for Development |  | 2023-10-18 08:29 | 2023-12-13 09:27 |  | FX_OCT_2023_3;FX_OCT_2023_2 |  | 9000 |  |  | 14400 | 5400 | Product FusionX | BA_DEC_1;CollateralModule;product | 18
Epic | PF-291 | Collateral Module ¦ Settings ¦ LTV Ratios ¦ Incorporate LTV additional fields | Dinesh Wickramaarachchi | MilleniN | Highest | Ready for Development |  | 2023-10-16 17:31 | 2023-12-12 22:32 |  |  |  | 57600 |  |  | 57600 | 0 | Product FusionX | CollateralModule;LeasingModule;LendingModule;product | 96
Epic | PF-680 | Collateral Module ¦ Collateral Onboarding ¦ Displaying Reference number instead of Collateral Ref | Naveen Rathnayake | Naveen Rathnayake | Highest | Ready for Development |  | 2023-10-13 11:01 | 2023-12-13 09:34 |  | FX_OCT_2023_3;FX3_OCT_2023_2 |  | 3600 |  |  | 7200 | 3600 | Product FusionX | BA_DEC_1;CollateralModule;product | 8
Epic | PF-1799 | Cash Module ¦ GL Entries ¦ Developing a new Functionality | VivekaI | VivekaI | Highest | Ready for Development |  | 2023-10-13 10:53 | 2023-12-05 15:23 |  |  |  | 28800 |  |  | 28800 | 0 | Product FusionX | BA_NOV_1;CashModule;product | 244
Epic | PF-650 | Collateral Module ¦ Collateral Onboarding ¦ Legal Opinion ¦ View/Display Added Documents. | Naveen Rathnayake | Naveen Rathnayake | Highest | Ready for Development |  | 2023-10-12 16:44 | 2023-12-13 09:30 |  | FX_OCT_2023_3;FX_OCT_2023_2 |  | 9000 |  |  | 14400 | 5400 | Product FusionX | BA_DEC_1;CollateralModule;product | 18
Epic | PF-2097 | CASA Module ¦ Reports OAC ¦ Saving portfolio report |  | BanchanaW | Highest | Ready for Development |  | 2023-10-10 09:50 | 2023-12-12 22:52 |  |  |  | 28800 |  |  | 14400 | 0 | Product FusionX | AccountsModule;KenyaDecember2023;product | 28
Epic | PF-1387 | All Modules ¦ Settings ¦ GL Definitions ¦ Charges Which recorded in Income account to be seperated | BandulaR | BandulaR | Highest | Abandoned |  | 2023-10-09 12:45 | 2023-11-29 14:09 |  | FX1_OCT_2023_3;FX1_OCT_2023_2 |  |  |  |  | 28800 | 28800 | Product FusionX | BA_DEC_1;BA_OCT_2_Candidate;KenyaDecember2023 | 44
Epic | PF-1389 | Common Settings Module ¦ GL Enquiry ¦ Financial GL transaction report & inquiry ¦ Developing a New Report & Enquiry | Achini Kalhari | BandulaR | Highest | Ready for Production | Done | 2023-10-09 12:44 | 2023-12-08 13:23 |  | FX1_OCT_2023_3;FX1_OCT_2023_2 | 3600 | 435600 |  | 0 | 100800 | 0 | Product FusionX | AccountsModule;KenyaDecember2023 | 116
Epic | PF-1900 | Account Module ¦ Dormant Account Management ¦ Suspend income accrual after dormant ¦ Developing a new Functionality | Theeksha Dumini | BandulaR | Highest | In UAT | Done | 2023-10-09 12:43 | 2023-12-13 11:47 |  | FX_OCT_2023_3;FX1_OCT_2023_2 |  | 172800 |  |  | 201600 | 28800 | Product FusionX | AccountsModule;GateKeepersCommited;KenyaDecember2023 | 104
Epic | PF-294 | Lending Module ¦ Settings ¦ Product Definitions ¦ Repayment Template Maintenance ¦ Developing a new Functionality | Dinesh Wickramaarachchi | BanchanaW | Highest | Ready for Development |  | 2023-10-09 08:58 | 2023-12-12 22:32 |  | Lending_FX_Oct_2023_2 | 28800 | 86400 |  | 0 | 57600 | 0 | Product FusionX | BA_NOV_2;LendingModule;product | 60
Epic | PF-1116 | Supplier Module ¦ Supplier Management ¦ Supplier integration with Fusion ¦ Developing New Integration | Amila Rathnayaka | Sampath Dimuthu Gallage | Highest | In Progress |  | 2023-10-06 10:19 | 2023-12-12 18:49 |  |  |  | 230400 |  |  | 345600 | 288000 | Product FusionX | Dec_2;KenyaDecember2023;UI/UX_Pending | 280
Epic | PF-2255 | Account Module ¦ Reports ¦ OAC ¦ Cheque Deposit detail report (Current & PDC) report ¦ Developing a New Report | Naveen Rathnayake | Sampath Dimuthu Gallage | Highest | Ready for Development |  | 2023-10-06 09:10 | 2023-12-12 22:52 |  |  |  | 100800 |  |  | 86400 | 0 | Product FusionX | AccountsModule;KenyaDecember2023;product | 44
Epic | PF-1493 | TD Module ¦ Reports ¦ Term Deposit Movement Report ¦ Developing a New Report | Rashmika Dolawatta | Randika Gunasekara | Highest | In UAT | Done | 2023-10-05 16:34 | 2023-12-15 17:13 |  |  |  | 86400 |  |  | 86400 | 57600 | Product FusionX | FDModule;KenyaDecember2023;Nov_2;QA_BA_Committed | 64
Epic | PF-2981 | Lending Module ¦ Interest Calculation ¦ Interest Tier Band Modification | Dinesh Wickramaarachchi | Asitha Abeysekara | Medium | To Do |  | 2023-10-05 09:48 | 2023-12-14 17:25 | [6 empty] | 57600 | 57600 | Product FusionX | BA_DEC_2;ClientKenya;LendingModule | 216
Epic | PF-2273 | TD Module ¦ Alert Management ¦ Alerts Generation ¦ Developing a new Functionality | PraweenAy | Randika Gunasekara | Highest | In Progress |  | 2023-10-03 09:25 | 2023-12-06 10:21 |  |  |  | 266400 |  |  | 14400 | 0 | Product FusionX | Dec_1;KenyaDecember2023 | 120
Epic | PF-2254 | Account Module ¦ Reports ¦ OAC ¦ OD Utilization And Activity Report ¦ Developing a New Report | BanchanaW | Naveen Rathnayake | Highest | Ready for Development |  | 2023-09-27 11:32 | 2023-12-15 11:37 |  | FX_SEPT_2023_1 |  | 115200 |  |  | 115200 | 0 | Product FusionX | AccountsModule;KenyaDecember2023;product | 60
Epic | PF-1662 | Account Module ¦ Reports ¦ OAC ¦ Accounts Opening Report ¦ Developing a New Report | BanchanaW | Naveen Rathnayake | Highest | Ready for Development |  | 2023-09-25 17:20 | 2023-12-08 12:38 |  | FX_SEPT_2023_1 |  | 61200 |  |  | 61200 | 0 | Product FusionX | AccountsModule;KenyaDecember2023;product | 45
Epic | PF-2229 | TD Module ¦ Manage Transaction ¦ Partial PreMature creation with Product Change ¦ Developing a new Functionality | Randika Gunasekara | Randika Gunasekara | Highest | Ready for Development |  | 2023-09-25 13:19 | 2023-12-12 22:52 |  |  |  | 115200 |  |  | 28800 | 0 | Product FusionX | AssetLine;FDModule;product | 120
Epic | PF-2093 | Account Module ¦ Reports ¦ OAC ¦ Stop Payments Report with reasons | Theeksha Dumini | Sampath Dimuthu Gallage | Highest | In Progress |  | 2023-09-25 10:28 | 2023-12-08 11:12 |  |  |  | 57600 |  |  | 57600 | 0 | Product FusionX | AccountsModule;Dec_1;KenyaDecember2023 | 60
Epic | PF-1914 | Account Module ¦ Reports ¦ OAC ¦ Fee Income Report ¦ Developing a New Report | Sandun Samadhi Bandara | Sampath Dimuthu Gallage | Highest | In Progress |  | 2023-09-22 12:27 | 2023-12-08 11:12 |  | FX_OCT_2023_3 |  | 28800 |  |  | 14400 | 0 | Product FusionX | AccountsModule;Dec_1;KenyaDecember2023 | 32
Epic | PF-1664 | Supplier Module ¦ Reports ¦ OAC ¦ Business introducer report ¦ Developing a New Report | BanchanaW | Sampath Dimuthu Gallage | Highest | In Progress |  | 2023-09-21 13:02 | 2023-12-08 11:12 |  |  |  | 115200 |  |  | 57600 | 0 | Product FusionX | BaWizards;Dec_1;KenyaDecember2023 | 64
Epic | PF-2915 | Lending Module ¦ Integration ¦ CRIB reporting ¦ Developing a new Functionality | Asitha Abeysekara | Asitha Abeysekara | Medium | To Do |  | 2023-09-21 08:37 | 2023-12-14 20:14 |  | Lending_FX_Oct_2023_2;Lending_FX_Oct_2023_1 | 57600 | 57600 |  | 0 | 28800 | 28800 | Product FusionX | BA_DEC_2;ClientKenya;LendingModule | 320
Epic | PF-1104 | Account Module ¦ Teller Management ¦ Non counter cash deposit ¦ Developing a new Functionality | BandulaR | Sampath Dimuthu Gallage | Highest | In Progress |  | 2023-09-20 13:50 | 2023-12-08 11:12 |  |  |  | 57600 |  |  | 203400 | 145800 | Product FusionX | AccountsModule;BA_NOV_2;Dec_2;KenyaDecember2023 | 156
Epic | PF-2089 | Account Module ¦ Charges Management ¦ Waive off Charges ¦ Developing a new Functionality | Naveen Rathnayake | Naveen Rathnayake | Highest | In Progress |  | 2023-09-18 16:07 | 2023-12-15 14:15 |  |  |  | 302400 |  |  | 316800 | 14400 | Product FusionX | AccountsModule;BA_DEC_1;Dec_2;KenyaDecember2023 | 336
Epic | PF-1899 | TD Module ¦ Reports ¦ Applied Interest Detail Report ¦ Developing a New Report | Udeshika Madushani Pushpakumara | BhagyaA | Highest | In UAT | Done | 2023-09-18 11:53 | 2023-12-13 11:52 |  | FX_OCT_2023_3;FX3_OCT_2023_2;FX3_OCT_2023_1 |  | 7200 |  |  | 7200 | 0 | Product FusionX | FDModule;GateKeepersCommited;KenyaDecember2023 | 56
Epic | PF-1121 | Accounts Module ¦ Transaction Management ¦ Banker's Cheque ¦ Developing a new Functionality | Sampath Dimuthu Gallage | Sampath Dimuthu Gallage | Highest | Ready for Development |  | 2023-09-14 09:15 | 2023-12-08 12:41 |  |  |  | 14400 |  |  | 86400 | 86400 | Product FusionX | AccountsModule;BA_NOV_2;KenyaDecember2023;product | 248
Epic | PF-2077 | Account Module ¦ Teller Management ¦ Miscellaneous Charge ¦ Developing a new Functionality | Gihan Abeykoon[IT/EKO/LOITS] | Sampath Dimuthu Gallage | Highest | In Progress |  | 2023-09-13 12:31 | 2023-12-15 10:49 |  |  |  | 86400 |  |  | 187200 | 187200 | Product FusionX | AccountsModule;BA_NOV_1;ClientKenya;Dec_2;KenyaDecember2023 | 240
Epic | PF-1131 | TD Module ¦ Validate Rate Limit maintenance in the Special Rate ¦ Developing a new Functionality | Asangi Dasanayaka | ShanikaPe | Highest | Ready for Development |  | 2023-09-07 13:34 | 2023-12-12 22:52 |  | FX_OCT_2023_3 |  | 100800 |  |  | 14400 | 0 | Product FusionX | AssetLine;FDModule;product | 151
Epic | PF-2224 | TD Module ¦ Interest Rate Maintenance ¦ Bulk Interest Rate Update & Confirmation ¦ Developing a new Functionality | Randika Gunasekara | ShanikaPe | Highest | In Progress |  | 2023-09-07 13:01 | 2023-12-06 08:50 |  |  |  | 2.1456e+06 |  |  | 100800 | 0 | Product FusionX | FDModule;KenyaDecember2023;Nov_2 | 212
Epic | PF-2277 | TD Module ¦ Manual Renewal ¦ Creation with Product Change ¦ Developing a new Functionality | Randika Gunasekara | ShanikaPe | Highest | In Progress |  | 2023-09-07 12:47 | 2023-12-03 20:29 |  |  |  | 172800 |  |  | 28800 | 0 | Product FusionX | AssetLine;Dec_1 | 156
Epic | PF-2020 | TD Module_Cheque printing for TD payments | Amal Hapuarachchi [IT/EKO/LOITS] | ShanikaPe | Medium | Abandoned | Done | 2023-09-07 12:38 | 2023-12-03 20:36 | [8 empty] | Product FusionX | AssetLine;Duplicated | 272
Epic | PF-829 | TD Module ¦ Trial Calculation ¦ Developing a new Functionality | Gihan Abeykoon[IT/EKO/LOITS] | ShanikaPe | Highest | Ready for Development |  | 2023-09-07 12:29 | 2023-12-12 22:52 |  |  |  | 86400 |  |  | 28800 | 0 | Product FusionX | FDModule;product | 138
Epic | PF-1287 | TD Module ¦ Manage Transaction ¦ External Interest Payment ¦ Feature to allowing Cheque payment | Madawa Milan | Randika Gunasekara | Highest | In UAT | Done | 2023-09-06 11:04 | 2023-12-13 12:55 |  |  |  | 842400 |  |  | 14400 | 0 | Product FusionX | FDModule;GateKeepersCommited;KenyaDecember2023;Nov_2 | 208
Epic | PF-1095 | TD Module ¦ Account Management ¦ Opening Account ¦ Adding Interest Posting details as a transfer to 3rd party system | Nishadi Hewawitharana | Randika Gunasekara | Highest | In UAT | Done | 2023-09-06 11:01 | 2023-12-15 17:31 |  |  |  | 968400 |  |  | 104400 | 86400 | Product FusionX | KenyaDecember2023;Nov_2;QA_BA_Committed | 208
Epic | PF-2228 | Account Module ¦ Credit Appraisal ¦ Select a Corporate guarantor in OD Appraisal ¦ Developing a new Functionality |  | ShanikaPe | Highest | In UAT | Done | 2023-08-29 14:25 | 2023-12-13 12:57 |  | FX_OCT_2023_3;Lending_FX_Sep_2023_2;Lending_FX_Oct_2023_2;Lending_FX_Sep_2023_1;Lending_FX_Oct_2023_1 | [6 empty] | Product FusionX | AccountsModule;CR;GateKeepersCommited;KenyaDecember2023;product | 16
Epic | PF-2274 | Account Module ¦ Credit Appraisal ¦ Display Liability Information in Appraisal ¦ Developing a new Functionality | Isuru Dilantha | ShanikaPe | Highest | In Progress |  | 2023-08-29 14:21 | 2023-12-15 10:46 |  | Lending_FX_Sep_2023_2;Lending_FX_Oct_2023_2;Lending_FX_Sep_2023_1;Lending_FX_Oct_2023_1 |  | 28800 |  |  | 28800 | 0 | Product FusionX | AccountsModule;Dec_1;KenyaDecember2023 | 96
Epic | PF-2230 | Account Module ¦ Lead Management ¦ Display Liabilities in Lead Creation ¦ Developing a new Functionality | chalani.koralalage | ShanikaPe | Highest | Ready for Development |  | 2023-08-29 14:02 | 2023-12-03 20:41 |  | Lending_FX_Sep_2023_2;Lending_FX_Oct_2023_2;Lending_FX_Sep_2023_1;Lending_FX_Oct_2023_1 |  | 28800 |  |  | 28800 | 0 | Product FusionX | AccountsModule;Dec_1;KenyaDecember2023 | 12
Epic | PF-1824 | Cash Module ¦ Multi-currency and cross currency transactions Inquiry ¦ Developing a new Functionality | Gihan Abeykoon[IT/EKO/LOITS] | VivekaI | Highest | In Definition |  | 2023-08-15 09:31 | 2023-12-08 21:48 | [8 empty] | Product FusionX | BA_DEC_1;CashModule;product | 96
Epic | PF-1825 | Cash Module ¦ Transaction exception inquiry ¦ Developing a new Functionality | Gihan Abeykoon[IT/EKO/LOITS] | VivekaI | Highest | In Definition |  | 2023-08-15 09:21 | 2023-12-08 21:47 | [6 empty] | 14400 | 14400 | Product FusionX | BA_DEC_1;CashModule;product | 80
Epic | PF-1770 | Cash Module ¦ Transfer Transaction Inquiry ¦ Developing a new Functionality | Gihan Abeykoon[IT/EKO/LOITS] | VivekaI | Highest | Ready for Development |  | 2023-08-15 09:20 | 2023-12-08 21:47 |  |  |  | 14400 |  |  | 14400 | 0 | Product FusionX | CashModule;product | 88
Epic | PF-1787 | Cash Module ¦ Inquiry ¦ Cash Withdrawal Inquiry ¦ Developing a new Functionality | Gihan Abeykoon[IT/EKO/LOITS] | VivekaI | Highest | In Progress |  | 2023-08-15 09:19 | 2023-12-03 23:35 |  |  |  | 158400 |  |  | 14400 | 0 | Product FusionX | BA_NOV_1;CashModule;InProgress;product | 88
Epic | PF-1788 | Cash Module ¦ Inquiry ¦ Cash Deposit Inquiry ¦ Developing a new Functionality | VivekaI | VivekaI | Highest | Ready for Development |  | 2023-08-15 09:19 | 2023-12-03 23:41 |  |  |  | 57600 |  |  | 28800 | 0 | Product FusionX | BA_NOV_1;CashModule;product | 72
Epic | PF-1789 | Cash Module ¦ Teller Management ¦ Rounding Off Entries Approval ¦ Developing a new Functionality | Gihan Abeykoon[IT/EKO/LOITS] | VivekaI | Highest | Ready for Development |  | 2023-08-14 14:20 | 2023-12-08 13:32 |  | FX_OCT_2023_3 |  | 14400 |  |  | 43200 | 28800 | Product FusionX | BA_NOV_2;CashModule;product | 92
Epic | PF-1838 | Cash Module ¦ Settings ¦ Transaction Event ¦ Developing a new Functionality | VivekaI | VivekaI | Highest | Ready for Development |  | 2023-08-13 19:44 | 2023-12-13 22:43 |  |  |  | 14400 |  |  | 14400 | 0 | Product FusionX | BA_DEC_1;CashModule;product | 88
Epic | PF-1853 | Cash Module ¦ Settings ¦ Transaction Sub Code ¦ Developing a new Functionality | VivekaI | VivekaI | Highest | Ready for Development |  | 2023-08-13 17:07 | 2023-12-13 22:44 |  |  |  | 14400 |  |  | 14400 | 0 | Product FusionX | BA_DEC_1;CashModule;product | 48
Epic | PF-1854 | Cash Module ¦ Settings ¦ Transaction Code ¦ Developing a new Functionality | VivekaI | VivekaI | Highest | Ready for Development |  | 2023-08-13 15:45 | 2023-12-13 22:41 |  |  |  | 14400 |  |  | 14400 | 0 | Product FusionX | BA_DEC_1;CashModule;product | 48
Epic | PF-1028 | Account Module ¦ Teller Management ¦ Inhouse Cheque Clearance ¦ New Option required for Cancelation | Sampath Dimuthu Gallage | Naveen Rathnayake | Highest | In Definition |  | 2023-08-03 11:18 | 2023-12-12 22:48 |  | FX_AUG_2023_1 |  |  |  |  | 72000 | 72000 | Product FusionX | AccountsModule;BA_DEC_1;product | 20
Epic | PF-2275 | TD Module ¦ Manage Transaction ¦ Interest Payment on a Specific Date ¦ Developing a new Functionality | Gihan Abeykoon[IT/EKO/LOITS] | Randika Gunasekara | Highest | In Progress |  | 2023-07-26 00:11 | 2023-12-06 11:27 |  |  |  | 345600 |  |  | 43200 | 0 | Product FusionX | Dec_2;FDModule;KenyaDecember2023 | 298
Epic | PF-1033 | Account Module ¦ Reports ¦ Cheque Book Detail Report ¦ Developing a New Report | Gihan Abeykoon[IT/EKO/LOITS] | Gihan Abeykoon[IT/EKO/LOITS] | Highest | In Definition |  | 2023-07-18 19:56 | 2023-12-15 09:19 |  | FX_AUG_2023_1;FX_JULY_2023_2;FX_AUG_2023_2 |  |  |  |  | 14400 | 14400 | Product FusionX | AccountsModule;BA_DEC_1;product | 46
Epic | PF-412 | Account Module ¦ Statement ¦ Single Statement Printing ¦ UI Modification | BandulaR | N Thanula Deemal | Highest | Ready for Development |  | 2023-07-18 07:54 | 2023-12-12 22:48 |  | FX_JULY_2023_2 |  | 14400 |  |  | 14400 | 0 | Product FusionX | AccountsModule;BA_NOV_1;product | 12
Epic | PF-401 | All Modules ¦ Setting ¦ New UI for oracle code mapping | Gihan Abeykoon[IT/EKO/LOITS] | Sampath Dimuthu Gallage | Highest | Ready for Development |  | 2023-07-10 15:21 | 2023-12-05 16:24 |  | FX_JULY_2023_1;FX_JULY_2023_2 |  | 14400 |  |  | 14400 | 0 | Product FusionX | BA_NOV_1;ProductSettings;comn-settings;product | 16
Epic | PF-782 | Lending Module ¦ Loan Account Management ¦ Backdated Transactions in Account Activation ¦ Developing a new Functionality | Asitha Abeysekara | BandulaR | Medium | To Do |  | 2023-06-27 07:59 | 2023-12-12 22:30 |  |  |  | 43200 |  |  | 43200 | 0 | Product FusionX | BA_NOV_2;LendingModule;product | 8
Epic | PF-2236 | Account Module ¦ 3rd Party Integrations ¦ M-PESA Mobile wallet integration ¦ Deposits to CASA - C2B API | Janaka Abesinghe [IT/EKO/LOITS] | Dinesh Wickramaarachchi | Highest | In Progress |  | 2023-06-26 14:29 | 2023-12-08 10:32 | [8 empty] | Product FusionX | Dec_2;KenyaDecember2023 | 80
Epic | PF-1023 | Account Module ¦ Cheque Book ¦ Include the audit Information ¦ Developing a new Functionality | Sampath Dimuthu Gallage | Gihan Abeykoon[IT/EKO/LOITS] | Highest | In Definition |  | 2023-06-26 13:55 | 2023-12-12 22:48 |  | FX_JULY_2023_1;FX_AUG_2023_1;FX_JULY_2023_2;FX_AUG_2023_2 |  |  |  |  | 28800 | 28800 | Product FusionX | AccountsModule;BA_DEC_1;product | 24
Epic | PF-1055 | Account Module ¦ Cheque Book Management ¦ Including a new Validation & Message | Naveen Rathnayake | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-06-23 17:50 | 2023-12-12 22:48 |  | FX_JULY_2023_1;FX_AUG_2023_1;FX_JULY_2023_2;FX_AUG_2023_2;FX_JUNE_2023_2 |  | 9000 |  |  | 14400 | 5400 | Product FusionX | AccountsModule;BA_DEC_1;product | 40
Epic | PF-1025 | Account Module ¦ Account Management ¦ Opening Account ¦ Include Toggle for Cheque Book Usage ¦ Developing a new Functionality | Piratheepan | Gihan Abeykoon[IT/EKO/LOITS] | Highest | In Definition |  | 2023-06-23 17:24 | 2023-12-15 08:59 |  | FX_JULY_2023_1;FX_AUG_2023_1;FX_JULY_2023_2;FX_AUG_2023_2;FX_JUNE_2023_2 |  |  |  |  | 36000 | 36000 | Product FusionX | AccountsModule;BA_DEC_1;product | 10
Epic | PF-388 | Account Module ¦ Account Management ¦ Account Opening ¦ Enable field to capture the OD Recovery Detail ¦ Enable new Feature | BandulaR | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-06-23 16:57 | 2023-12-12 22:48 |  | FX_JULY_2023_1;FX_AUG_2023_1;FX_JULY_2023_2;FX_AUG_2023_2;FX_JUNE_2023_2 |  | 82800 |  |  | 14400 | 0 | Product FusionX | AccountsModule;BA_NOV_1;product | 38
Epic | PF-25 | Payment Module ¦ Master Definitions ¦ Finance account Mapping with GL ¦ Developing a new Functionality | Randika Gunasekara | MilleniN | Medium | Ready for Development |  | 2023-06-09 11:56 | 2023-12-12 17:14 |  | FX_AUG_2023_1 |  | 21600 |  |  | 21600 | 0 | Product FusionX | BA_NOV_2;PaymentModule;product | 24
Epic | PF-441 | Account Module ¦ Charge Negotiation ¦ Developing a new Functionality ¦ Back End | Gihan Abeykoon[IT/EKO/LOITS] | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-06-06 20:21 | 2023-12-12 22:48 |  | FX_JULY_2023_1;FX_AUG_2023_1;FX_JUNE_2023_1;FX_JULY_2023_2;FX_JUNE_2023_2 |  | 14400 |  |  | 14400 | 0 | Product FusionX | AccountsModule;BA_NOV_1;product | 168
Epic | PF-17 | Payment Module ¦ Master Definitions ¦ Expense Type ¦ Developing a new Functionality | Randika Gunasekara | MilleniN | Medium | Ready for Development |  | 2023-05-30 10:46 | 2023-12-05 23:26 |  | November_1 |  | 7200 |  |  | 21600 | 14400 | Product FusionX | BA_NOV_2;PaymentModule;product | 24
Epic | PF-428 | Account Module ¦ Settings ¦ Product Definition ¦ Enable a Sub Product level Eligibility validation | BandulaR | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-05-26 09:34 | 2023-12-12 22:48 |  | FX_JULY_2023_1;FX_MAY_2023_2;FX_AUG_2023_1;FX_JUNE_2023_1;FX_JULY_2023_2;FX_AUG_2023_2;FX_JUNE_2023_2 |  |  |  |  | 14400 | 14400 | Product FusionX | AccountsModule;BA_NOV_1;product | 52
Epic | PF-381 | Account Module ¦ Fund Reservation Validation ¦ Enable a new Rule | Gihan Abeykoon[IT/EKO/LOITS] | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-05-25 19:32 | 2023-12-12 22:48 |  | FX_JULY_2023_1;FX_MAY_2023_2;FX_AUG_2023_1;FX_JUNE_2023_1;FX_JULY_2023_2;FX_AUG_2023_2;FX_JUNE_2023_2 | [6 empty] | Product FusionX | AccountsModule;product | 32
Epic | PF-1083 | TD Module ¦ Product Management ¦ Upfront Interest Payment ¦ Developing a new Functionality | PraweenAy | Randika Gunasekara | Highest | In Progress |  | 2023-05-20 21:17 | 2023-12-14 09:26 |  |  |  | 583200 |  |  | 453600 | 0 | Product FusionX | Dec_2;KenyaDecember2023;TD_Module;product | 404
Epic | PF-391 | Account Module ¦ Standing Order Management ¦ Standing Order Creation ¦ Enable new Condition as Variable for STO Execution | BandulaR | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2023-05-16 14:12 | 2023-12-12 22:48 |  |  |  | 43200 |  |  | 43200 | 0 | Product FusionX | AccountsModule;BA_NOV_1;product | 144
Epic | PF-778 | Lending Module ¦ Calculate Pre-EMI ¦ Developing a new Functionality | Dinesh Wickramaarachchi | TharinduBan | Highest | Ready for Development |  | 2023-05-15 09:01 | 2023-12-12 22:32 |  | Lending_FX_May_2023_2 | 43200 | 86400 | 43200 | 0 | 86400 | 0 | Product FusionX | LendingModule;product | 40
Epic | PF-999 | Account Module ¦ Manage Account ¦ Account Balance Enquiry Screen ¦ Developing a new Functionality | BandulaR | Gihan Abeykoon[IT/EKO/LOITS] | Highest | In Definition |  | 2023-04-27 13:44 | 2023-12-13 17:53 |  | FX_OCT_2023_3;FX_JULY_2023_1;FX_MAY_2023_2;FX_AUG_2023_1;FX_OCT_2023_2;FX_JUNE_2023_1;FX_JULY_2023_2;FX_AUG_2023_2;FX_MAY_2023_1;FX_JUNE_2023_2 |  |  |  |  | 3600 | 3600 | Product FusionX | AccountsModule;BA_DEC_1;product | 112
Epic | PF-52 | Payment Module ¦ Create Payment ¦ Payables ¦ Payment Creation ¦ Developing a new Functionality | BhagyaA | Randika Gunasekara | Medium | In Definition |  | 2023-04-27 10:06 | 2023-12-05 23:09 |  |  |  | 100800 |  |  | 100800 | 0 | Product FusionX | BA_NOV_2;PaymentModule;TechTitans;UI/UX_Pending;product | 524
Epic | PF-47 | Payment Module ¦ Invoice Creation ¦ Standard Invoice Upload ¦ Developing a new Functionality | Dinuja Theeraj | Randika Gunasekara | Medium | In Definition |  | 2023-04-27 09:54 | 2023-12-05 23:23 |  |  |  | 57600 |  |  | 43200 | 0 | Product FusionX | BA_NOV_2;PaymentModule;UI/UX_Pending;product | 250
Epic | PF-21 | Payment Module ¦ Master Definitions ¦ Sub Cost Centers ¦ Developing a new Functionality | Randika Gunasekara | Randika Gunasekara | Medium | Ready for Development |  | 2023-04-27 09:24 | 2023-12-05 23:32 |  |  |  | 7200 |  |  | 21600 | 14400 | Product FusionX | BA_NOV_2;PaymentModule;product | 28
Epic | PF-19 | Payment Module¦ Master Definitions ¦ Invoice Template Mapping ¦ Developing a new Functionality | Randika Gunasekara | Randika Gunasekara | Medium | Ready for Development |  | 2023-04-27 09:20 | 2023-12-05 23:29 |  |  |  | 7200 |  |  | 21600 | 14400 | Product FusionX | BA_NOV_2;PaymentModule;product | 24
Epic | PF-18 | Payment Module ¦ Master Definitions ¦ Invoice Types ¦ Developing a new Functionality | Dinuja Theeraj | Randika Gunasekara | Medium | In Definition |  | 2023-04-27 09:16 | 2023-12-05 23:31 | [6 empty] | 21600 | 21600 | Product FusionX | BA_NOV_2;PaymentModule;product | 24
Epic | PF-1847 | Cash Module ¦ Central Cash Management ¦ Teller Transaction GL Mapping ¦ Developing a new Functionality | VivekaI | VivekaI | Highest | In Definition |  | 2023-04-03 16:04 | 2023-12-13 22:37 | [6 empty] | 28800 | 28800 | Product FusionX | BA_DEC_1;CashModule;product | 64
Epic | PF-566 | Lending Module ¦ Loan Account Management ¦ Account Maintenance ¦ Adding Follow-up Comments in Contract ¦ Developing a new Functionality | Dinesh Wickramaarachchi | rajitha kumara | Highest | Ready for Development |  | 2023-03-16 08:34 | 2023-12-12 22:32 |  |  |  | 28800 |  |  | 57600 | 28800 | Product FusionX | BA_DEC_1;LendingModule;product | 100
Epic | PF-439 | COB Module_Order of arranging contact/identification/address types | Naveen Rathnayake | TharinduBan | Highest | Ready for Development |  | 2023-02-28 16:02 | 2023-12-12 22:52 |  | FX_MARCH_2023_1 | 28800 | 43200 | 28800 | 0 | 43200 | 0 | Product FusionX | BA_NOV_1;CustomerOnBoardingModule;product | 52
Epic | PF-425 | Account Module ¦ Settings ¦ Transaction Configuration ¦ Enable Transaction blocking by customer type | Randika Gunasekara | Randika Gunasekara | Highest | Ready for Development |  | 2023-02-15 12:46 | 2023-12-12 22:48 |  |  |  | 32400 |  |  | 43200 | 10800 | Product FusionX | AccountsModule;BA_NOV_1;product | 72
Epic | PF-396 | Common Settings Module ¦ Customer Age Eligibility Details ¦ Developing a new Functionality | rajitha kumara | ShanikaPe | Highest | Ready for Development |  | 2023-02-10 10:33 | 2023-12-12 22:52 |  |  |  | 14400 |  |  | 28800 | 14400 | Product FusionX | BA_NOV_1;CustomerOnBoardingModule;product | 92
Epic | PF-1061 | Account Module ¦ Teller Management ¦ Operation ¦ Developing a New Functionality to upload a document for fund transfer creation | Naveen Rathnayake | Sampath Dimuthu Gallage | Highest | Ready for Development |  | 2023-02-06 11:01 | 2023-12-12 22:48 |  | FX_JULY_2023_1;FX_APRIL_2023_2;FX_JULY_2023_2;FX_MAY_2023_1;FX_FEBRUARY_2023_1;FX_FEBRUARY_2023_2;FX_MAY_2023_2;FX_AUG_2023_1;FX_MARCH_2023_1;FX_JUNE_2023_1;FX_MARCH_2023_2;FX_AUG_2023_2;FX_JUNE_2023_2;FX_APRIL_2023_1 |  | 9000 |  |  | 14400 | 5400 | Product FusionX | AccountsModule;BA_DEC_1;product | 24
Epic | PF-1058 | Account Module ¦ Fund Reservation Management ¦ Include UI Modification | Naveen Rathnayake | Sampath Dimuthu Gallage | Highest | Ready for Development |  | 2023-02-06 10:52 | 2023-12-12 22:48 |  | FX_JULY_2023_1;FX_APRIL_2023_2;FX_JULY_2023_2;FX_MAY_2023_1;FX_FEBRUARY_2023_1;FX_FEBRUARY_2023_2;FX_MAY_2023_2;FX_AUG_2023_1;FX_MARCH_2023_1;FX_JUNE_2023_1;FX_MARCH_2023_2;FX_AUG_2023_2;FX_JUNE_2023_2;FX_APRIL_2023_1 |  | 9000 |  |  | 14400 | 5400 | Product FusionX | AccountsModule;BA_DEC_1;product | 32
Epic | PF-1852 | Cash Module ¦ Teller Definition ¦ Teller Limit Controller Approval ¦ Developing a new Functionality | VivekaI | VivekaI | Highest | In Definition |  | 2023-02-03 16:25 | 2023-12-13 22:36 | [6 empty] | 14400 | 14400 | Product FusionX | BA_DEC_1;CashModule;product | 168
Epic | PF-435 | Account Module ¦ PD Cheque cancellation ¦ Developing a new Functionality | Gihan Abeykoon[IT/EKO/LOITS] | Thushara Withanage | Highest | Ready for Development |  | 2023-01-30 11:00 | 2023-12-12 22:48 |  | FXTD_FEB_2023_1 |  | 86400 |  |  | 86400 | 0 | Product FusionX | AccountsModule;BA_NOV_1;UI/UX_Pending;product | 120
Epic | PF-1782 | Cash Module ¦ Teller Inquiries ¦ Transaction Inquiry ¦ Developing a New Functionality | VivekaI | VivekaI | Highest | Ready for Development |  | 2023-01-20 17:19 | 2023-12-13 22:38 |  |  |  | 86400 |  |  | 28800 | 0 | Product FusionX | BA_DEC_1;CashModule;product | 240
Epic | PF-1160 | Cash Module ¦ Reports ¦ Teller Wise Cash Balance Report ¦ Developing a New Report | Gihan Abeykoon[IT/EKO/LOITS] | VivekaI | Highest | Done | Done | 2023-01-20 17:16 | 2023-12-04 00:07 |  |  |  | 223200 |  |  | 158400 | 0 | Product FusionX | BA_NOV_1;CashModule;product | 68
Epic | PF-1783 | Cash Module ¦ Reports ¦ Branch wise cash Summary Report ¦ Developing a New Report | Dinuja Theeraj | VivekaI | Highest | Ready for Development |  | 2023-01-20 17:12 | 2023-12-03 23:34 |  |  |  | 57600 |  |  | 14400 | 0 | Product FusionX | BA_DEC_1;CashModule;product | 82
Epic | PF-1316 | Cash Module ¦ Reports ¦ Cash Currier Report ¦ Developing a New Report | PraweenAy | VivekaI | Highest | In Progress |  | 2023-01-20 17:10 | 2023-12-03 23:43 |  |  |  | 165600 |  |  | 14400 | 14400 | Product FusionX | BA_NOV_1;CashModule;InProgress;product | 50
Epic | PF-1785 | Cash Module ¦ Reports ¦ Bank Deposit Report ¦ Developing a New Report | Gihan Abeykoon[IT/EKO/LOITS] | VivekaI | Highest | Done | Done | 2023-01-20 17:06 | 2023-12-03 23:35 |  |  |  | 295200 |  |  | 208800 | 72000 | Product FusionX | CashModule;product | 68
Epic | PF-1784 | Cash Module ¦ Reports ¦ Cheque in Hand Report ¦ Developing a New Report | Gihan Abeykoon[IT/EKO/LOITS] | VivekaI | Highest | Ready for Development |  | 2023-01-20 17:05 | 2023-12-03 23:34 |  |  |  | 180000 |  |  | 36000 | 0 | Product FusionX | CashModule;product | 68
Epic | PF-1786 | Cash Module ¦ Reports ¦ Daily Branch Cash Summary Report ¦ Developing a New Report | VivekaI | VivekaI | Highest | Ready for Development |  | 2023-01-20 16:57 | 2023-12-03 23:45 |  |  |  | 28800 |  |  | 28800 | 0 | Product FusionX | CashModule;product | 28
Epic | PF-1823 | Cash Module ¦ Report ¦ Daily Teller Cash Summary Report ¦ Developing a New Report | VivekaI | VivekaI | Highest | Abandoned |  | 2023-01-20 16:55 | 2023-12-08 21:50 | [6 empty] | 14400 | 14400 | Product FusionX | BA_DEC_1;CashModule;product | 36
Epic | PF-1001 | Cash Module ¦ Reports ¦ Daily Teller Transaction Report ¦ Developing a New Report | VivekaI | VivekaI | Highest | Ready for Development |  | 2023-01-20 16:49 | 2023-12-04 00:09 | [6 empty] | 14400 | 14400 | Product FusionX | CashModule;product | 48
Epic | PF-1168 | Cash Module ¦ Passbook ¦ Savings Passbook Printing ¦ Developing a new Functionality | VivekaI | VivekaI | Medium | In Definition |  | 2023-01-20 16:13 | 2023-12-13 12:17 |  |  |  | 14400 |  |  | 28800 | 14400 | Product FusionX | BA_DEC_1;CashModule;product | 208
Epic | PF-1804 | Cash Module ¦ Teller other transactions ¦ Reverse Transactions ¦ Developing a new Functionality | Nusri Samath | VivekaI | Highest | In Progress |  | 2023-01-20 16:10 | 2023-12-12 22:52 |  |  |  | 547200 |  |  | 86400 | 0 | Product FusionX | BA_NOV_1;CashModule;InProgress;product | 128
Epic | PF-1039 | Collateral Module ¦ Reports ¦ Collateral Register ¦ Developing a New Report | BandulaR | ShanikaPe | Highest | In Definition |  | 2022-12-27 14:07 | 2023-12-12 22:52 | [6 empty] | 14400 | 14400 | Product FusionX | BA_DEC_1;CollateralModule;product | 16
Epic | PF-423 | Common Settings Module ¦ Common Settings ¦ Geo hierarchy Master Definition ¦ Developing a new Functionality | Sampath Dimuthu Gallage | Randika Gunasekara | Highest | Ready for Development |  | 2022-12-12 13:14 | 2023-12-12 22:52 |  |  |  | 36000 |  |  | 72000 | 36000 | Product FusionX | BA_NOV_1;comn-settings;product | 10
Epic | PF-421 | COB Module ¦ Pending approval ¦ Search option | Naveen Rathnayake | Sampath Dimuthu Gallage | Highest | Ready for Development |  | 2022-12-05 11:27 | 2023-12-12 22:52 |  |  |  | 14400 |  |  | 14400 | 0 | Product FusionX | BA_NOV_1;CustomerOnBoardingModule;product | 30
Epic | PF-1003 | Account Management ¦ Cheque Book ¦ Status Update Confirmation ¦ Developing a new Functionality | Randika Gunasekara | Randika Gunasekara | Highest | In Definition |  | 2022-11-27 22:54 | 2023-12-13 09:37 |  |  |  | 28800 |  |  | 28800 | 0 | Product FusionX | AccountsModule;BA_DEC_1;InnoWave;product | 80
Epic | PF-68 | Accounts Module ¦ Settings ¦ Product Definition ¦ Sub Product Inactivation ¦ Enable New Eligibility | Gihan Abeykoon[IT/EKO/LOITS] | Randika Gunasekara | Highest | Ready for Development |  | 2022-11-27 22:32 | 2023-12-12 22:48 |  |  |  | 14400 |  |  | 14400 | 0 | Product FusionX | AccountsModule;BA_NOV_1;product | 30
Epic | PF-1150 | Cash Module ¦ Central Cash Management ¦ Branch Parameters ¦ Developing a new Functionality | Dinuja Theeraj | VivekaI | Highest | Ready for Development |  | 2022-11-16 11:25 | 2023-12-04 12:07 |  |  |  | 14400 |  |  | 43200 | 28800 | Product FusionX | BA_DEC_1;CashModule;product | 60
Epic | PF-382 | Account Module ¦ Cheque Books ¦ Pending Cheque Book ¦ Sorting the List detail | Naveen Rathnayake | Gihan Abeykoon[IT/EKO/LOITS] | Highest | Ready for Development |  | 2022-11-10 01:46 | 2023-12-12 22:48 |  | FX_JANUARY_2023_1;FX_JULY_2023_1;FX_APRIL_2023_2;FX_JANUARY_2023_2;FX_NOVEMBER_2022_2;FX_JULY_2023_2;FX_MAY_2023_1;FX_FEBRUARY_2023_1;FX_FEBRUARY_2023_2;FX_DECEMBER_2022_1;FX_MAY_2023_2;FX_AUG_2023_1;FX_MARCH_2023_1;FX_JUNE_2023_1;FX_MARCH_2023_2;FX_AUG_2023_2;FX_NOVEMBER_2022_1;FX_JUNE_2023_2;FX_DECEMBER_2022_2;FX_APRIL_2023_1 |  | 14400 |  |  | 28800 | 14400 | Product FusionX | AccountsModule;BA_NOV_1;product | 14
Epic | PF-1148 | Account Module ¦ Bulk cash/cheque uploading option via batch ¦ Developing a new Functionality | rajitha kumara | Sampath Dimuthu Gallage | Medium | Ready for Development |  | 2022-11-08 13:18 | 2023-12-04 17:34 |  | FX_DECEMBER_2022_1;FX_NOVEMBER_2022_2;FX_JULY_2023_2;FX_NOVEMBER_2022_1;FX_DECEMBER_2022_2 | 172800 | 208800 |  | 0 | 36000 | 0 | Product FusionX | AccountsModule;BA_DEC_1;MetaWave;Production | 108
Epic | PF-1042 | Collateral Module ¦ Reports ¦ Asset Cancellation Details ¦ Developing a New Report | BandulaR | Naveen Rathnayake | Highest | In Definition |  | 2022-11-01 08:29 | 2023-12-12 22:52 |  | FX_NOVEMBER_2022_1 |  |  |  |  | 14400 | 14400 | Product FusionX | BA_DEC_1;CollateralModule;product | 16
Epic | PF-1165 | Collateral Module ¦ Reports ¦ Block or Freeze Details Report ¦ Developing a New Report | Naveen Rathnayake | Naveen Rathnayake | Highest | Ready for Development |  | 2022-10-31 16:38 | 2023-12-13 10:02 |  | FX_AUG_2023_1;FX_AUG_2023_2;FX_NOVEMBER_2022_1 |  | 5400 |  |  | 14400 | 9000 | Product FusionX | BA_DEC_1;CollateralModule;product | 54
Epic | PF-1796 | Cash Module ¦ Till Cash Deposits ¦ Term Deposit Receipts ¦ Developing a new Functionality | Rashmika Dolawatta | VivekaI | Highest | Ready for Development |  | 2022-09-11 23:47 | 2023-12-03 23:55 |  |  |  | 36000 |  |  | 14400 | 0 | Product FusionX | CashModule;product | 136
Epic | PF-1797 | Cash Module ¦ Till Cash Deposits ¦ CASA Account Deposits ¦ Developing a new Functionality | VivekaI | VivekaI | Highest | Ready for Development |  | 2022-09-11 22:38 | 2023-12-12 22:52 |  |  |  | 28800 |  |  | 28800 | 0 | Product FusionX | BA_NOV_2;CashModule;product | 192
Epic | PF-1790 | Cash Module ¦ Teller Cash Management ¦ Transfer Cash Or Cheque Till To Vault ¦ Developing a new Functionality | Theeksha Dumini | BanchanaW | Highest | In UAT | Done | 2022-09-02 21:05 | 2023-12-08 13:32 |  | FX_OCT_2023_3 |  | 273600 |  |  | 72000 | 0 | Product FusionX | CashModule;product | 68
Epic | PF-1791 | Cash Module ¦ Teller cash management ¦ Inter Teller Cash Transfers ¦ Developing a new Functionality | Rashmika Dolawatta | BanchanaW | Highest | In Progress |  | 2022-09-02 21:02 | 2023-12-04 00:04 |  |  |  | 453600 |  |  | 28800 | 0 | Product FusionX | BA_NOV_1;CashModule;InProgress;product | 116
Epic | PF-1170 | Cash Module ¦ Branch Teller Operations ¦ Savings Account Fund Transfers ¦ Developing a new Functionality | Senitha Perera | BanchanaW | Highest | Ready for Development |  | 2022-09-02 20:59 | 2023-12-12 22:52 |  |  |  | 43200 |  |  | 14400 | 0 | Product FusionX | CashModule;product | 112
Epic | PF-1793 | Cash Module ¦ Branch Teller Operations ¦ CASA Account Withdrawals ¦ Developing a new Functionality | Dinuja Theeraj | BanchanaW | Highest | Ready for Development |  | 2022-09-02 20:57 | 2023-12-13 22:39 |  |  |  | 14400 |  |  | 43200 | 28800 | Product FusionX | BA_NOV_2;CashModule;product | 352
Epic | PF-1792 | Cash Module ¦ Branch teller operations ¦ Validate the Cheque withdrawal ¦ Developing a new Functionality | Senitha Perera | BanchanaW | Highest | Done | Done | 2022-09-02 20:55 | 2023-12-04 00:03 |  |  |  | 590400 |  |  | 316800 | 0 | Product FusionX | BA_NOV_1;CashModule;product | 112
Epic | PF-1795 | Cash Module ¦ Till Cash Withdrawals ¦ Withdrawal ¦ Rounding Off Entries ¦ Developing a new Functionality | Rashmika Dolawatta | BanchanaW | Highest | In Progress |  | 2022-09-02 20:50 | 2023-12-03 23:55 |  |  |  | 201600 |  |  | 100800 | 0 | Product FusionX | BA_NOV_1;CashModule;InProgress;product | 88
Epic | PF-1794 | Cash Module ¦ Till Cash Withdrawals ¦ Withdrawal ¦ Cash Coins Or Notes Exchange ¦ Developing a new Functionality | Senitha Perera | BanchanaW | High | Ready for Development |  | 2022-09-02 20:47 | 2023-12-15 11:41 |  |  |  | 57600 |  |  | 57600 | 0 | Product FusionX | CashModule;product | 48
Epic | PF-1120 | Cash Module ¦ Branch Teller Operations ¦ General Direct Payments ¦ Developing a new Functionality |  | BanchanaW | Highest | Ready for Development |  | 2022-09-02 20:35 | 2023-12-13 23:35 |  |  |  | 28800 |  |  | 72000 | 43200 | Product FusionX | BA_NOV_2;CashModule;product | 72
Epic | PF-1067 | Cash Module ¦ Branch Teller Operations ¦ Utility Bill Payment ¦ Developing a new Functionality | PraweenAy | BanchanaW | Highest | In Progress |  | 2022-09-02 20:27 | 2023-12-12 22:52 |  |  |  | 392400 |  |  | 57600 | 0 | Product FusionX | BA_NOV_1;CashModule;InProgress;product | 128
Epic | PF-1798 | Cash Module ¦ Till Cash Deposit Transactions ¦ Deposit ¦ Developing a new Functionality | Romesh Shanaka | BanchanaW | Highest | In Progress |  | 2022-09-02 20:21 | 2023-12-12 22:52 |  |  |  | 316800 |  |  | 57600 | 0 | Product FusionX | BA_NOV_1;CashModule;InProgress;product | 96
Epic | PF-1800 | Cash Module ¦ Branch Vault Fund Transactions ¦ Balancing Transactions ¦ Developing a new Functionality | Dinuja Theeraj | BanchanaW | Highest | Ready for Development |  | 2022-09-02 20:14 | 2023-12-08 13:31 |  |  |  | 28800 |  |  | 28800 | 0 | Product FusionX | BA_DEC_1;CashModule;product | 180
Epic | PF-1801 | Cash Module ¦ Branch Vault Fund Operations ¦ Funds withdrawals from banks ¦ Developing a new Functionality | Thiloshana Gamage | BanchanaW | Highest | In UAT | Done | 2022-09-02 20:06 | 2023-12-03 23:51 |  | FX_OCT_2023_3 |  | 208800 |  |  | 208800 | 14400 | Product FusionX | CashModule;product | 62
Epic | PF-1802 | Cash Module ¦ Branch Vault Fund Transactions ¦ Accept Teller To Teller Transfers ¦ Developing a new Functionality | Thiloshana Gamage | BanchanaW | Highest | In UAT | Done | 2022-09-02 19:56 | 2023-12-08 13:31 |  | FX_OCT_2023_3 |  | 129600 |  |  | 100800 | 7200 | Product FusionX | CashModule;product | 44
Epic | PF-1163 | Cash Module ¦ Accept Teller Cash or Cheques Transfers ¦ Developing a new Functionality | VivekaI | BanchanaW | Highest | In Definition |  | 2022-09-02 19:53 | 2023-12-12 16:52 |  |  |  | 14400 |  |  | 14400 | 0 | Product FusionX | BA_DEC_1;CashModule;product | 112
Epic | PF-1665 | Cash Module ¦ Branch Vault Fund Operations ¦ Fund Transfer ¦ Developing a new Functionality | Dinuja Theeraj | BanchanaW | Highest | In Definition |  | 2022-09-02 19:08 | 2023-12-15 14:23 |  |  |  | 28800 |  |  | 28800 | 0 | Product FusionX | BA_DEC_1;CashModule;product | 48
Epic | PF-1777 | Cash Module ¦ Branch Vault Fund Operations ¦ Cash Transfer To Tellers ¦ Developing a new Functionality | PraweenAy | BanchanaW | Highest | Ready for Development |  | 2022-09-02 19:03 | 2023-12-04 00:09 |  |  |  | 28800 |  |  | 28800 | 0 | Product FusionX | BA_NOV_1;CashModule;product | 72
Epic | PF-62 | Cash Module ¦ Exception Handling ¦ Transaction Exception Approval ¦ Developing a new Functionality | Gihan Abeykoon[IT/EKO/LOITS] | BanchanaW | Medium | To Do |  | 2022-09-02 18:48 | 2023-12-15 01:15 |  | Sprint_1 |  |  |  |  | 28800 | 28800 | Product FusionX | CashModule;product | 8
Epic | PF-1781 | Cash Module ¦ Branch Vault Fund Operations ¦ Transaction Reversal ¦ Developing a new Functionality | Thiloshana Gamage | BanchanaW | Highest | In UAT | Done | 2022-09-02 18:19 | 2023-12-03 23:44 |  | FX_OCT_2023_3 |  | 187200 |  |  | 72000 | 0 | Product FusionX | CashModule;product | 56
Epic | PF-1074 | Cash Module ¦ Cash Courier option ¦ Developing a New Report | VivekaI | BanchanaW | Highest | Ready for Development |  | 2022-09-02 16:57 | 2023-12-12 22:52 |  |  |  | 28800 |  |  | 57600 | 28800 | Product FusionX | BA_NOV_2;CashModule;product | 116
Epic | PF-1803 | Cash Module ¦ Branch Vault Fund Operations ¦ Bank Deposits Cash or Cheque ¦ Developing a new Functionality | Rashmika Dolawatta | BanchanaW | Highest | Done | Done | 2022-09-02 16:54 | 2023-12-03 23:50 |  |  |  | 472200 |  |  | 14400 | 0 | Product FusionX | CashModule;product | 112
Epic | PF-1779 | Cash Module ¦ Branch Vault Fund Transactions ¦ Agreeing the Vault Balance ¦ Developing a new Functionality | Sashike Karunaratne | BanchanaW | Highest | Done | Done | 2022-09-02 16:41 | 2023-12-04 00:10 |  |  |  | 244800 |  |  | 43200 | 0 | Product FusionX | BA_NOV_1;CashModule;product | 136
Epic | PF-1778 | Cash Module ¦ Daily Transactions ¦ Open/Close Tills/Vaults ¦ Developing a new Functionality | Nusri Samath | BanchanaW | Highest | Ready for Development |  | 2022-09-02 16:37 | 2023-12-04 00:21 |  |  |  | 388800 |  |  | 14400 | 0 | Product FusionX | CashModule;product | 130
Epic | PF-1780 | Cash Module ¦ Cash and Payment ¦ Main teller float IN ¦ Developing a new Functionality | Dinuja Theeraj | BanchanaW | Highest | Ready for Development |  | 2022-09-02 16:32 | 2023-12-08 13:33 |  |  |  | 28800 |  |  | 115200 | 86400 | Product FusionX | BA_NOV_2;CashModule;product | 92
Epic | PF-1161 | Cash Module ¦ Teller Definitions ¦ Assign Tills ¦ Developing a new Functionality | prageeth shan | BanchanaW | Highest | In Progress |  | 2022-09-02 16:16 | 2023-12-07 14:19 | [8 empty] | Product FusionX | BA_NOV_1;CashModule;InProgress;product | 48
Epic | PF-16 | Payment Module ¦ Master Definitions ¦ Payment Category ¦ Developing a new Functionality | Randika Gunasekara | BanchanaW | Medium | Ready for Development |  | 2022-09-02 13:45 | 2023-12-05 21:20 |  |  |  | 43200 |  |  | 43200 | 0 | Product FusionX | BA_NOV_1;PaymentModule;product | 24
Epic | PF-414 | Common Settings Module ¦ Common Settings ¦ Chanel Level Definition ¦ Developing a new Functionality | BandulaR | BanchanaW | Highest | Ready for Development |  | 2022-08-18 12:56 | 2023-12-12 22:52 |  |  |  | 10800 |  |  | 43200 | 32400 | Product FusionX | BA_NOV_1;ProductSettings;comn-settings;product | 32
Epic | PF-1047 | ATM Module ¦ Reports ¦ Developing Standard Reports to Handle The ATM | Randika Gunasekara | Randika Gunasekara | Highest | In Definition |  | 2022-08-01 10:17 | 2023-12-13 16:55 |  | FX_OCT_2023_3;FX_AUG_2023_1;FX_OCT_2023_2 |  | 14400 |  |  | 14400 | 0 | Product FusionX | ATMModule;BA_DEC_1;product | 64
Epic | PF-2231 | TD Module ¦ Security Document Re-Print Approval ¦ Developing a new Functionality | IsharaNad | Randika Gunasekara | Highest | In UAT | Done | 2021-10-24 17:24 | 2023-12-15 18:15 |  | FX_OCT_2023_3 |  | 28800 |  |  | 86400 | 57600 | Product FusionX | FDModule;KenyaDecember2023;Nov_2;QA_BA_Committed | 64